## Product Backlog
Priority | Backlog Item | Area | Related User Stories | Priority Class | Responsible
1 | Set up Node.js project | Foundation | US-20 | Must Have
2 | Set up Neon PostgreSQL database | Foundation | US-01–US-10 | Must Have
3 | Configure Sequelize | Foundation | US-01–US-10 | Must Have
4 | Create Coin model | Data model | US-01–US-06 | Must Have
5 | Create Email model | Data model | US-07–US-10 | Must Have
6 | Create Coin CRUD scripts | Administration | US-01–US-04 | Must Have
7 | Create Email CRUD scripts | Administration | US-07–US-10 | Must Have
8 | Add Zod validation for Coin scripts | Validation | US-01–US-06, US-17 | Must Have
9 | Add Zod validation for Email scripts | Validation | US-07–US-10, US-17 | Must Have
10 | Integrate CoinLore REST API | Monitoring | US-11 | Must Have
11 | Retrieve coin prices | Monitoring | US-11 | Must Have
12 | Implement price-range checking | Monitoring | US-05, US-06, US-12 | Must Have
13 | Integrate Gmail SMTP | Notification | US-13 | Must Have
14 | Implement email notifications | Notification | US-13, US-14 | Must Have
15 | Create main worker script | Monitoring | US-15 | Must Have
16 | Configure environment variables/secrets | Security | US-18 | Must Have
17 | Create GitHub Actions workflow | Automation | US-16 | Must Have
18 | Configure scheduled execution | Automation | US-15, US-16 | Must Have
19 | Test complete workflow | Testing | US-20 | Must Have